## Sheet1
Project Name | [5 empty] | Business Lead |  |  | Monica Joyner |  | Data Architect | Debasis Chatterjee
Project Deliverable |  | Data Warehouse/Business Intelligence (DW/BI) Solution for Fudgemart |  |  |  | Project Manager |  |  | Jo Vivian |  | ETL Architect | Monica Joyner
Scope Statement | [5 empty] | Business Analyst |  |  | Austin Beller |  | BI Architect | Levi Peckham
Start Date |  | 2020-01-19 | End Date |  | 2020-03-26 |  | Overall Project Progress |  |  |  | On Schedule/On Budget
At Risk? | Task Name |  |  | Assigned To | Start Date | End Date |  | Due Date | Duration (Days) | Status
Project Milestone 01 - Project Document
N | Assemble a Project Charter |  |  | Monica | 2020-01-19 | 2020-01-22 |  | 2020-01-30 | 3 | Complete
N | Devise a Project Plan |  |  | Jo | 2020-01-19 | 2020-01-23 |  | 2020-01-30 | 4 | Complete
N | Outline Functional Requirements |  |  | Levi, Austin, Debasis | 2020-01-19 | 2020-01-23 |  | 2020-01-30 | 4 | Complete
N | Overview which business processes you will model from those functional requirements and explain their business value |  |  | Levi, Austin, Debasis | 2020-01-19 | 2020-01-25 |  | 2020-01-30 | 6 | Complete
Project Milestone 02 - High level dimensional modeling worksheet
N | Bus Matrix |  |  | Levi, Austin, Debasis | 2020-01-26 | 2020-02-15 |  | 2020-02-20 | 20 | In Progress/On time
N | Attributes and Metrics |  |  | Levi, Austin, Debasis | 2020-01-26 | 2020-02-15 |  | 2020-02-20 | 20 | In Progress/On time
N | Peer Review worksheet |  |  | Jo, Monica | 2020-02-15 | 2020-02-16 |  | 2020-02-20 | 1 | Not Started
N | Outline issues |  |  | Jo, Monica | 2020-02-15 | 2020-02-17 |  | 2020-02-20 | 2 | Not Started
Project Milestone 03 - Detail level dimensional modeling worksheet & SQL Implementation
Worksheet |  |  |  |  | 2020-02-21 | 2020-02-29 |  | 2020-03-12 | 8 | Not Started
N | Contains fully completed dimensions and facts |  |  |  | 2020-02-21 | 2020-02-28 |  | 2020-03-12 | 7 | Not Started
N | Identifies Sources for your source-to-target map |  |  |  | 2020-02-21 | 2020-02-28 |  | 2020-03-12 | 7 | Not Started
N | Should be used to generate a SQL schema for your data warehouse |  |  |  | 2020-02-21 | 2020-02-28 |  | 2020-03-12 | 7 | Not Started
N | Peer Review worksheet |  |  |  | 2020-02-21 | 2020-02-29 |  | 2020-03-12 | 8 | Not Started
Data Warehouse on SQL Server |  |  |  |  | 2020-03-01 | 2020-03-08 |  | 2020-03-12 | 7 | Not Started
N | Follow Consistent Conventions |  |  |  | 2020-03-01 | 2020-03-08 |  | 2020-03-12 | 7 | Not Started
N | Adopts techniques learned in the course, such as use of staging and enterprise bus |  |  |  | 2020-03-01 | 2020-03-08 |  | 2020-03-12 | 7 | Not Started
Project Milestone 04 - Final Deliverable
Initial ETL done in SSIS |  |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
N | Source-to-target map |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
N | SSIS package to stage data |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
N | SSIS package to load to DW from stage |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
N | ETL Documentation |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
N | Source to target map |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
N | Screenshot of data flows |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
N | Explanation of ETL patterns |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
N | Data quality of survivorship rules |  |  |  | 2020-03-13 | 2020-03-19 |  | 2020-03-26 | 6 | Not Started
Business Intelligence |  |  |  |  | 2020-03-13 | 2020-03-22 |  | 2020-03-26 | 9 | Not Started
N | SSAS cubes on analysis services server |  |  |  | 2020-03-13 | 2020-03-22 |  | 2020-03-26 | 9 | Not Started
N | BI Dashboard or application in Power BI and/or Excel |  |  |  | 2020-03-13 | 2020-03-22 |  | 2020-03-26 | 9 | Not Started
N | BI Documentation |  |  |  | 2020-03-13 | 2020-03-22 |  | 2020-03-26 | 9 | Not Started
N | Goal of analytics |  |  |  | 2020-03-13 | 2020-03-22 |  | 2020-03-26 | 9 | Not Started
N | Type of BI |  |  |  | 2020-03-13 | 2020-03-22 |  | 2020-03-26 | 9 | Not Started
Presentation and Demo |  |  |  |  | 2020-03-23 | 2020-03-25 |  | 2020-03-26 | 2 | Not Started
N | 5-minute executive presentation overviewing DW and BI |  |  |  | 2020-03-23 | 2020-03-25 |  | 2020-03-26 | 2 | Not Started
N | 5-minute demo of BI application |  |  |  | 2020-03-23 | 2020-03-25 |  | 2020-03-26 | 2 | Not Started
N | Demo in class |  |  |  | 2020-03-23 | 2020-03-25 |  | 2020-03-26 | 2 | Not Started
Formulas:
Start Date = [Start Date, row below]
Business Lead = [Business Lead, row below]
Due Date = [Due Date, row below]