## Sheet1
Project Name | [5 empty] | Business Lead |  | Monica Joyner |  | Data Architect | Debasis Chatterjee
Project Deliverable |  | Data Warehouse/Business Intelligence (DW/BI) Solution for Fudgemart |  |  |  | Project Manager |  | Jo Vivian |  | ETL Architect | Monica Joyner
Scope Statement | [5 empty] | Business Analyst |  | Austin Beller |  | BI Architect | Levi Peckham
Start Date |  | 2020-01-19 | End Date |  | 2020-03-26 |  | Overall Project Progress |  |  | On Schedule/On Budget
At Risk? | Task Name |  |  | Assigned To | Start Date | End Date |  | Duration (Days) | Status
N | Assemble a Project Charter |  |  | Monica | 2020-01-19 |  |  | 7 | In Progress/On Time
N | Devise a Project Plan |  |  | Jo | 2020-01-19 |  |  | 7 | In Progress/On Time
N | Outline Functional Requirements |  |  | Levi, Austin, Debasis | 2020-01-19 |  |  | 7 | In Progress/On Time
N | Overview which business processes you will model from those functional requirements and explain their business value |  |  | Levi, Austin, Debasis | 2020-01-19 |  |  | 7 | In Progress/On Time